## Project Settings
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Javier Mesa
Start Date | mar 18, 2017 05:51:51 PM
Completion Date | mar 19, 2017 05:23:31 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:53 PM el 25/03/2017

## Overall Metrics
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 28.2 | 16.6 | 24.5
Planned Time | 0.28889 |  | 0.74028
Actual Tiempo |  | 0.27778 | 0.78889
CPI (Cost-Performance Index) |  |  | 0.94
% Reuse | 18.6% | 22.7% | 13.6%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 0 | 0 | 0
Total Defects/KLOC or equivalent | 34.1 | 18 | 30.2
Yield % | 66.7% | 100% | 71.4%
Code Review Rate | 902 | 256 | 567
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:52 PM el 25/03/2017

## Program Size
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 151 | 151 | 369
Deleted (D) | 100 | 52 | 226
Modified (M) | 10 | 23 | 42
Added (A) | 186 | 88 | 421
Reused (R) | 54 | 55 | 89
Added and Modified (A+M) | 196 | 111 | 463
Total Size (T) | 291 | 242 | 653
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 223 | 308 | 742
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:54 PM el 25/03/2017

## Time In Phase
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.064583 | 0.091667 | 0.20625 | 26.1%
DiseÃ±o | 0.045833 | 0.023611 | 0.10417 | 13.2%
RevisiÃ³n de DiseÃ±o | 0.0048611 | 0.0069444 | 0.015972 | 2.02%
CodificaciÃ³n | 0.10556 | 0.081944 | 0.26806 | 34%
RevisiÃ³n de CodificaciÃ³n | 0.0090278 | 0.018056 | 0.034028 | 4.31%
CompilaciÃ³n | 0.026389 | 0.010417 | 0.057639 | 7.31%
Pruebas | 0.018056 | 0.022222 | 0.054167 | 6.87%
Postmortem | 0.014583 | 0.022917 | 0.048611 | 6.16%
Total | 0.28889 | 0.27778 | 0.78889
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:55 PM el 25/03/2017

## Defects Injected
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.56 | 0 | 1 | 7.14%
DiseÃ±o | 3.33 | 1 | 7 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 2.78 | 1 | 6 | 42.9%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 6.67 | 2 | 14
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:55 PM el 25/03/2017

## Defects Removed
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.56 | 1 | 2 | 14.3%
CodificaciÃ³n | 3.89 | 0 | 7 | 50%
RevisiÃ³n de CodificaciÃ³n | 0 | 1 | 1 | 7.14%
CompilaciÃ³n | 2.22 | 0 | 4 | 28.6%
Pruebas | 0 | 0 | 0 | 0%
Total | 6.67 | 2 | 14
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:55 PM el 25/03/2017

## Defect Removal Efficiency
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 4.53 | 6 | 5.22
Defects/Hour - Code Review | 0 | 2.31 | 1.22
Defects/Hour - Compile | 3.47 | 0 | 2.89
Defects/Hour - Test | 0 | 0 | 0
DRL (DLDR/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Code Review/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Compile/UT) | #VALUE! | #DIV/0! | #DIV/0!
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:56 PM el 25/03/2017